## Slide 1
Digital Transformation Strategy 2027
STATUS REPORT
31st July 2026

## Slide 2
8
Sessions Held
✔
Governance Established
Overall Status- Report Update Covers
1
01
Meetings Held — 8 Sessions
02
Workstream Progress — Program Portal
Salesforce Discovery & Governance
04
Mobile App & AI Agents Reviewed
Key Decisions & Risks
Action Items & Next Steps
Programme at a Glance
WGS Digital Transformation 2027 — Internal Status Update
3
5
2
4
6

## Slide 3
Meetings Held — Week of 31 July 2026
8 sessions completed | MOMs issued | Actions in progress
Salesforce
01
Salesforce Kickoff & Ways of Working
Attendees
WGS · Salesforce Professional Services
Key Outcomes
Salesforce engagement kicked off; governance model, delivery methodology and timeline aligned
Governance framework and Agile methodology agreed; RACI reviewed and responsibilities clarified across both teams
Jira confirmed as single source of truth; sprint cadence and Confluence documentation process established
Weekly governance and Friday reporting agreed; WGS to own SIT/UAT and deployments with Salesforce support
02
Enterprise Architecture & Membership Discovery
Attendees
WGS · Salesforce Professional Services
Key Outcomes
Full walkthrough of the WGS digital ecosystem and end-to-end Partner & Membership module completed
Salesforce confirmed as System of Record; membership, nomination, registration and speaker journeys reviewed
Existing object model, integrations and future TenTwenty Community Portal integration into Salesforce reviewed
Discovery progressed from Enterprise Architecture into detailed functional module walkthroughs
04
Mobile Application Review
Attendees
WGS · TenTwenty
Key Outcomes
Mobile wireframes and AI Agent concepts presented
UX and branding approach discussed
WGS to review application screens and provide consolidated feedback
Unified branding across AI Agents to be confirmed
TenTwenty : Program Portal . Community Portal . Mobile App
03
Program Portal Workflow Workshops
Parties
WGS · TenTwenty
Key Outcomes
Program, Session and Participant workflows reviewed in detail
Approval gates and operational processes documented
Workflow optimisation discussions completed
Figma workflow diagrams initiated for the new approval journey
✔ Complete
✔ Complete
✔ Complete
✔ Complete

## Slide 4
Workstream Focus — Program Portal
Governance established · Salesforce discovery progressing into functional module walkthroughs
Delivery Timeline
1
Requirements
Gathering
Complete
2
Architecture
& Design
In Progress
3
Development
In Progress
4
Data Migration
& Sanity
Not Started
5
UAT &
Go-Live
Not Started
Current Status
Salesforce project commenced with governance framework, Agile methodology, sprint framework and Jira governance established
Discovery progressed from Enterprise Architecture into functional module walkthroughs, with Membership user journeys successfully documented
Program Portal approval workflows progressed significantly through multiple working sessions with TenTwenty
End-to-end Program, Session and Participant operational journeys being documented and redesigned for greater automation
Mobile application wireframes and AI Agent concepts presented, with WGS feedback now pending before design finalisation
Salesforce now has a comprehensive understanding of both the technical architecture and the core business processes
Open Decisions
Final approval workflow diagrams pending completion by TenTwenty
MuleSoft deployment model (Cloud vs On-Prem) and Community Portal integration approach to be confirmed
Mobile application branding alignment to be confirmed across all AI Agents; final UI consistency with Jeeraj’s website design to be agreed
Immediate Next Steps
Receive final workflow diagrams from TenTwenty and formally approve workflow documentation
Submit consolidated mobile application feedback
Continue remaining functional discovery and module walkthroughs; complete 1020 partner onboarding
Finalise MuleSoft deployment approach and begin detailed solution design
Workstream Focus — Program Portal

## Slide 5
Salesforce — Current Status Update
31 July 2026 · Discovery & Solution Design
⇄
Current Status
Discovery phase progressing well following kickoff. Governance framework, Ways of Working and sprint methodology defined, with delivery model and workshop schedule agreed.
📄
Integration Platform
Salesforce confirmed as central System of Record. MuleSoft integration planning underway; deployment model (Cloud vs On-Prem) remains an open architectural decision.
Governance
Agile methodology and sprint framework agreed. Jira confirmed as single source of truth, RACI clarified, and weekly governance with Friday status reporting established.
📖
Project Direction
Discovery is progressing successfully across technical and functional streams, with Solution Design confirmed as the next phase.
Discovery Progress
Technical discovery (Enterprise Architecture) and functional discovery (Membership module) both completed. User journey discovery progressing successfully across core business processes.
Next Step
Continue discovery workshops, complete workflow definition, finalise solution architecture and commence implementation planning.

## Slide 6
Key Decisions & Risks
Items Requiring Management Attention Or Tracking
Open Decisions
Item
Detail
Status
Workflow Sign-Off
Final approval workflows to be reviewed and approved once TenTwenty delivers the completed diagrams.
Pending
Integration Architecture
MuleSoft deployment model (Cloud vs On-Prem) and Community Portal authentication/integration approach to be confirmed.
In Progress
Mobile Branding
Confirm unified branding approach across AI Agents and mobile experience.
In Progress
Programme Risks
Level
Risk
Mitigation
Medium
Final workflow approval delayed
Weekly validation sessions continue until sign-off is achieved.
Medium
Mobile UX feedback outstanding
WGS to complete application review and provide consolidated feedback.
Low
Infrastructure architecture dependent on MuleSoft decision
Finalise MuleSoft deployment model and complete remaining functional walkthroughs before Solution Design.
Key Decisions & Risks

## Slide 7
Key Decisions & Risks
Action Items & Next Steps
All open actions — Week of 31 July 2026 | 9 action items
Action Item
Owner
Target
Status
Deliver final Program Portal workflow diagrams
TenTwenty
Next Week
In Progress
Review and approve workflow diagrams
WGS
Next Week
Pending
Continue functional discovery: International Delegation, International Organisation & Guest/Speaker modules
Salesforce & WGS
Ongoing
In Progress
Complete detailed solution architecture
Salesforce
Ongoing
In Progress
Review mobile application wireframes
WGS
Next Week
Pending
Submit consolidated screen-recorded mobile feedback
WGS
Next Week
Pending
Confirm unified branding approach across AI Agents
WGS & TenTwenty
Next Workshop
Pending
Decide MuleSoft deployment model (Cloud vs On-Prem)
WGS & Salesforce
Next Week
Pending
Confirm RACI and finalise Jira & governance documentation; complete 1020 partner onboarding
WGS & Salesforce
Next Week
Pending